## TestPlan
Test Planner and Tracker |  |  | (Team Account: s261-05a) | Team 1: ‘The D Is Silent’
Test No. ID | Related Systems / User Story | Pre-conditions | Test Description (steps) | Expected Outcome | R1 Outcome (color code cell background) | R2 beta Outcome (color code cell background) | R2 Outcome (color code cell background)
1 | user wants to create an account | user is on registration page | register user - user enters information, -username already taken, -invalid email adress, -passwords don’t match,- passwords case sensistive,- email already taken, information entered appropriately | account activation email sent or report why acount was not activated | successful
2 | user wants to view profile information | user on homepage | Sign in first or if signed in click the profile link. | profile information displayed on the profile page | First name and last name are missing, Username and email are visible, editing not available at this time
3 | user wants to check if a tool is available | user has account and tool is in database | Sign in, go to Tools then Browse. | Item should be shown as a ration'd number | Works but of rough design. Needs refinement
4 | user wants to rent a tool | user has account and tool is in database | Sign in, go to Tools, Browse, click on Item, | System accounts for checked out item. | Not Implemented yet
5 | user wants to return a tool | user and owner have exchanged a tool | user and owner- Sign in, go to Profile, Click on item in inventory and click return item | Item stripped from users account and returned to master warehouse | Not Implemented yet
6 | user wants to add a tool to the tool shed | user has account | Sign in, go to Tools, Click Add, and enter information, then click submit. | Item added to database without problem. | successful
7 | user wants to check availability date | user has account and tool is in database | Sign in, go to Tools, Click on item. Check date. | Item will show data of avaibility | Not Implemented yet | Not Implemented yet
8 | user wants to view a tool and information about tool | user has account and tool is in database | Sign in, go to Tools, Browse. Check regarding information | Item list shows tool info | successful
9 | item shared only in one location at a time | user has account | Sign in, go to Tools, Click on item, try to borrow an already borrowed tool, and borrow an avalable tool | will not be able to borrow already borrowed tool and availble tool will become unavailable and the location will change | Not Implemented yet
10 | Set dates for tool availability. | user is viewing a tool they have borrowed or own | edit the avalability information | estimated return date changed, or if owned avalability date changed | Not Implemented yet | Not Implemented yet
11 | User is notified if someone wishes to borrow a tool | user (not the owner account) on tool page | user fills out borrow form information and submits it | email is sent telling owner a tool has been requested | Not Implemented yet | Not Implemented yet
12 | unregister tool | user has account and tool is in database | Sign in, go to Tools, click unregister tool that is avalable | tool should be removed form database | Not Implemented yet | Not Implemented yet
13 | unregister shared tool | user has account and tool is in database currently being shared | Sign in, go to Tools, click unregister tool that is being shared and unavalable | tool should remain in database and and user should be notified that you cannot remove a tool that is currently being shared | Not Implemented yet | Not Implemented yet
14 | search for a tool by location | user has account | Sign in, go to Tools, click search, enter location | all tools in that location are returned | Not Implemented yet | Not Implemented yet
15 | search for a tool by name | user has account | Sign in, go to Tools, click search, enter name | all tools by that name are returned | Not Implemented yet | Not Implemented yet
16 | edit profile information | user on home page signed into account | click the profile button, click edit profile, enter ifnormation, click submit, | information is edited and new information is view on profile page | Not Implemented yet | Not Implemented yet
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Instructions
Test plan Instructions
It is particularly important that you create a substantial set of Acceptance
Tests. These are tests based on the requirements document. Each acceptance
test should describe an operation to be performed by the user, and the
expected outcomes from that operation. The objective is to define a
comprehensive set of tests that between them cover all the features in the
requirements document. The tests should preferably cover all the frequent
"normal use" scenarios, as well as commonly occurring exception scenarios.
Each acceptance test must be described as a set of user instructions for
performing the test, much like a user manual. The outcomes description
specifies how the user knows whether the test succeeded or failed. The
reason for defining acceptance tests early in the life-cycle is to
facilitate "test-driven development". Developers can look at the acceptance
tests that their module must satisfy, and thereby know exactly what behavior
is expected from their module. Make sure to update these if/when
requirements change. Make sure to follow the suggested format.

## Monopoly Example
Monopoly Test Planner and Tracker (example)
Game in test mode implies that the tester can control the outcome of the dice roll - assume dice roll can exceed 12 for testing.
Note that some of the test cases require previous test cases to be completed as a precondition.
Acceptance tests
Test No. | User Story covered | Preconditions | Test Description | Expected Outcome | R1 Outcome | R2 Outcome
1 | Move Player | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester1 | Player 1 Dice Roll Total : 5 Player 1 End Turn | Player 1 is located at Reading Railroad cell.
2 | Move Player | Test 1 completed | Player 1 Dice Roll Total : 5 Player 1 End Turn | Player 1 is located on Jail cell.
3 | Move Players in Turns | Game is in test mode. Game is in initial state. Number of Players: 2 Player 1 Name: Tester1 Player 2 Name: Tester2 | Player 1 Dice Roll: 5 Player 1 End Turn | Player 1 is located at Reading Railroad
|  |  | Player 2 Dice Roll: 3 Player 2 End Turn | Player 2 is located at Baltic Avenue
4 | Pass Go | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 39 Player 1 End Turn | Player 1 is located at Boardwalk
|  |  | Verify Player 1 bank balance | Player 1 has $1500
5 | Pass Go | Game is in test mode Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 40 Player 1 End Turn | Player 1 is located on GO cell
|  |  | Verify Player 1 bank balance | Player 1 has $1700 | Go money paid out only after passing GO, not when it is reached.
6 | Pass Go | Game is in test mode. Game is in initial state. Number of Players: 1 Player 1 Name: Tester 1 | Player 1 Dice Roll: 41 Player 1 End Turn | Player 1 is located at Mediterranean Avenue
|  |  | Verify Player 1 bank balance | Player 1 has $1700